## Main-All Programs
CalGEM_NTO 2020-04 - COVID-19 Pandemic Requests
Item | Facility (Operator) | Location | Program | Request Date | Request Type | Request | Regulatory Required Deadline | CalGEM Response/Status
1 | E&B Natural Resources | Poso Creek Oil Field | UIC | 2020-05-05 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing on cyclic steam and steamflood wells in Poso Creek Oil Field. | Yes | Denied
2 | Kern River Holdings II, LLC. | Kern River Field | UIC | 2020-05-06 | Delay Mechanical Integrity Testing (MIT) schedule and update of 3D Steamflood Stimulation Model. | Request for deadline extension of mechanical integrity testing on several wells. Request for deadline extension of 3D Steamflood Stimulation Model update on UIC Project 34000159. | Yes | Denied
3 | Hathaway LLC. | Edison Oil Field, Bakersfield | UIC | 2020-05-07 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing on UIC Project 22203012 for API’s 03054082, 03054083, 03054084, 03054085, 03054086, 03054248, 03054249, 03054250. | Yes | Clarified: No Special Relief Necessary
4 | Warren Resources/Warren E&P, Inc. | 625 E. Anaheim Street, Wilmington, CA 90744 | UIC | 2020-05-08 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of RA Tracer Surveys. | No | Clarified: No Special Relief Necessary
5 | E&B Natural Resources | Livermore, Tejon Hills, South Belridge, Cymric, McKittrick, Blackwells Corner Fields | UIC | 2020-05-08 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing on several water disposal wells. | Yes | Clarified: No Special Relief Necessary
6 | California Resources Corporation (CRC) | Rincon, South Mountain Fields | UIC | 2020-05-11 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing on well API's 11103286, 11101693, 11101687, 11122087, 11122249. | Yes | Clarified: No Special Relief Necessary
7 | California Resources Corporation (CRC) | Bardsdale Field, Ventura | UIC | 2020-05-18 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing on well API 11100368. | Yes | Denied
8 | E&B Natural Resources | San Joaquin Valley | UIC | 2020-05-15 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing on several cyclic steam and steamflood wells. | Yes | Denied
9 | Chevron North America Exploration and Production | Kern River Field | UIC | 2020-05-26 | Delay well remediation. | Request for extension of MIT failure remediation for 19 wells. | Yes | Withdrawn by Operator
10 | San Joaquin Facilities Management, Inc. | Ten Section, Canfield, Fruitvale, Cal Canal Fields | UIC | 2020-06-02 | Delay Project By Project review data submission. | Request to delay Project By Project review data submission for UIC Projects 09500001, 10606004, 76603005, 25609013, 25609024. | No | Approved
11 | E&B Natural Resources | 1608 Norris Road, Bakersfield, CA 93308 | UIC | 2020-05-29 | Delay continuous pressure monitoring. | Request for deadline extension of continuous pressure monitoring. | Yes | Revised by Operator
12 | Southern California Gas Company | Aliso Canyon, Honor Rancho, La Goleta, and Playa Del Rey storage fields | UGS | 2020-03-23 | Stay of Enforcement | Request that CalGEM stay enforcement of the casing inspection and pressure testing required to be completed on October 1, 2020. | No | Denied
13 | Rockpoint Gas Storage | Wild Goose storage field | UGS | 2020-03-23 | Stay of Enforcement | Request that CalGEM stay enforcement of the casing inspection and pressure testing required to be completed on October 1, 2020. | No | Under Consideration
14 | Lodi Gas Storage | Lodi Gas and Kirby Hills storage fields | UGS | 2020-03-23 | Stay of Enforcement | Request that CalGEM stay enforcement of the casing inspection and pressure testing required to be completed on October 1, 2020. | No | Under Consideration
15 | Pacific Gas and Electric Company | McDonald Island, Los Medanos, and Pleasant Creek storage fields | UGS | 2020-03-24 | Stay of Enforcement | Request that CalGEM stay enforcement of the casing inspection and pressure testing required to be completed on October 1, 2020. | No | Under Consideration
16 | Gill Ranch Storage | Gill Ranch storage field | UGS | 2020-03-25 | Stay of Enforcement | Request that CalGEM stay enforcement of the casing inspection and pressure testing required to be completed on October 1, 2020. | No | Under Consideration
17 | Southern California Gas Company | Aliso Canyon, Honor Rancho, La Goleta, and Playa Del Rey storage fields | UGS | 2020-05-18 | Stay of Enforcement | Request that CalGEM grant a six-month extension of the stay enforcement of the casing inspection and pressure testing required to be completed on October 1, 2020. | No | Under Consideration
18 | Hathaway LLC (H2175) | Inland District, Kern County. Northeast Edison, Jasmin, and Edison fields. | Idle Well | 2020-03-20 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting a 90 day extension from April 1, 2020 to complete testing and/or abandonment on two (2) well. | Yes | Approved
19 | Harvest (11072) | N/A, Request for fee submittal date deferment | Idle Well | 2020-04-06 | Fee Extension length | Operator is requesting to have fees deferred until December 31, 2020. Operator provided with an extension until July 1, 2020 to submit payment. | Yes | Denied
20 | Fourstar (F1540) | N/A, Request for fee submittal date deferment | Idle Well | 2020-04-20 | Fee Extension length | Operator email is requesting a fee extension "for the foreseeable future". Tracking log notes a 6 to 12 month extension. | Yes | Denied
21 | Signal Hill (S3625) | N/A, Request for fee submittal date deferment | Idle Well | 2020-04-21 | Fee Extension length | Operator is requesting a 45-60 day deferment via a phone call 4-21-2020. The Idle Well Program sent an email to the operator documenting that an extension was requested. This email did not document the 45-60 day length of the extension request. | Yes | Approved
22 | Terracore (11108) | N/A, Request for fee submittal date deferment | Idle Well | 2020-04-22 | Fee Extension length | Operator is requesting a six (6) month deferral of fees until November 1, 2020. | Yes | Denied
23 | HT Olsen (O1477) | N/A, Request for fee submittal date deferment | Idle Well | 2020-04-30 | Fee Extension length | Operator requesting a 113 day deferment until August 21, 2020 for fees and a waiving of idle well fees for a well plugged and abandoned in 2019 on 2019 IWMP. | Yes | Denied
24 | Angus (A3070) | N/A, Request for fee submittal date deferment | Idle Well | 2020-05-01 | Fee Extension length | Operator is requesting an open ended fee deferment. States that they would like to work with CalGEM. | Yes | Denied
25 | HBOC (H4325) | N/A, Request for fee submittal date deferment | Idle Well | 2020-05-01 | Fee Extension length | Operator is requesting an open ended fee deferment. States that they would like to work with CalGEM. | Yes | Denied
26 | E&B (E0100) | N/A | Idle Well | 2020-05-01 | Idle Well Management Plan (IWMP) extension length | Operator is requesting a deferment of the compliance due date of the 2020 IWMP until July 1, 2021. | Yes | Denied
27 | Bellaire (B3077) | Inland District, Kern County; Edison and Kern Front fields. | Idle Well | 2020-05-01 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting a deferment to the end of 2020 for four (4 )MITs and C/O Tags due April 1, 2020 . Additionally, operator is requesting a one year deferment to April 1, 2022 for seven (7) MITs and C/O Tags to be due April 1, 2021. | Yes | Denied
28 | Aera (A0610) | Inland, Coastal, and Southern Districts | Idle Well | 2020-05-01 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting a deferment in the form of a three (3) month hiatus for all completion of testing. All compliance due dates would be changed to July 1 of each year between 2020 and 2025. | Yes | Denied
29 | Pacific Coast Energy Company LP (B6127) | Coastal and Southern Districts | Idle Well | 2020-05-04 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting that no testing be due in 2020. Testing would be completed in Compliance Years 2021 through 2024 at a cumulative rate of completion of 22.5%, 45%, 72.5%, and 100%. | Yes | Denied
30 | Maranatha Petroleum (M1600) | N/A, Request for fee submittal date deferment | Idle Well | 2020-05-05 | Fee Extension length | Operator is requesting a 45 day deferment for fees. | Yes | Approved
31 | Drilling & Production Co. (D4300) | Inland District, Kern County; Midway Sunset and Tejon fields. | Idle Well | 2020-05-07 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting that Compliance Year 2019 benchmarks be deferred until the end Compliance Year 2020. This would result in 15% of subject wells being brought into compliance by April 1, 2021. Operator intends to P&A proposed idle well in lieu of testing for 2019 requirement. | Yes | Denied
32 | California Petroleum Group, Inc. (11166) | N/A, Request for fee submittal date deferment | Idle Well | 2020-05-11 | Fee Extension length | Operator is requesting a two month deferment of fees. | Yes | Approved
33 | Matrix (M2600) | Southern and Inland Districts | Idle Well | 2020-05-11 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting an extension to remediate and/or partially plug four well tested as part of the CWP in 2019. These wells are or will be subject to the 15-Year Engineering Analysis. Regulation requires that a well idle for 15 years or more demonstrate mechanical integrity to be viable to return to use. Because these well failed their MITs, they are initially non-viable. Regulation allows the operator at least 30 days to submit additional information to demonstrate that the well is viable to return to use. In this case, that additional information would be a passing MIT. Operator is offering to conduct a fluid level every two months. Additionally, operator is requesting to defer nine (9) required casing pressure tests, cleanout tags, and subsequent 15-Year Engineering Analyses due in 2020 until the end of 2021 to allow for oil prices to recover. | Yes | Denied
34 | Zynergy (10463) | N/A, Request for fee submittal date deferment | Idle Well | 2020-05-14 | Fee Extension length | Operator is requesting a deferment of 2019 fees until August 2020 and a deferment of 2020 fees until September 2020. | Yes | Denied
35 | Crimson Resource Management (C9035) | N/A | Idle Well | 2020-05-19 | Idle Well Management Plan (IWMP) extension length | Operator is requesting a deferment the requirement to eliminate Long-term idle wells on the IWMP until January 1, 2021. | Yes | Denied
36 | Crimson Resource Management (C9035) | Coastal and Inland Districts | Idle Well | 2020-05-19 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting to change testing benchmarks by extending compliance period an additional year. | Yes | Denied
37 | Mountain View (11064) | Inland District, Kern County, Mountain View field | Idle Well | 2020-05-20 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting no enforcement action for 60 days from May 1, 2020 for failure to testing in accordance with the CWP one well. Testing was due April 1, 2020. Well is the operator's only well subject to the CWP. Well is not a LTIW. | Yes | Approved
38 | Signal Hill (S3625) | Northern and Southern Districts | Idle Well | 2020-05-21 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting that less that the required number of Casing Pressure Test and Cleanout Tags under the CCR 1772.1.4 (CWP) and CCR 1772.1 (Idle well testing for wells that became idle after 4-1-19) be completed. They state that they will complete as much as economically and operationally feasible. Any deficiencies in the number of wells tested will be made up in subsequent years | Yes | Denied
39 | E&B (E0100) | Southern, Northern, Coastal, and Inland Districts | Idle Well | 2020-06-16 | Idle Well Testing Compliance Work Plan (CWP) extension length | Operator is requesting change yearly benchmark percentages and extend the CWP an extra two years. | Yes | Denied
40 | Terracore Operating Company LLC | Cat Canyon | UIC | 2020-05-15 | Delay well remediation. | Terracore Operating Company LLC (TOC) requests a 6 month (180 day) time extension on the following wells to complete remediation or plugback. 0408321291, 0408321872, 0408321276, 0408321235 | Yes | Approved
41 | The Termo Company | Oak Canyon, Mountain View Oil, Ojai, Aliso Canyon, South Mountain, Long Beach Fields | UIC | 2020-06-11 | Delay Project By Project review data submission. | The Termo Company requested deadline extensions for submitting the UIC project data submission. (Project No. 508001, Project No. 49006004, Project No. 5201705, Project No. 0100007, Project No. 714003, Project No. 41400001) | No | Approved
42 | EnviroTech Consultants, Inc. | Fruitvale Field | UIC | 2020-06-24 | Delay Project By Project review data submission. | Operator requested the extension of data submission for Dole’s Fruitvale UIC project update (UIC Project#25609016 Water Disposal). Plan to submit the update by 9/30/2020. | No | Approved
43 | Chevron North America Exploration and Production | 9525 Camino Media, Bakersfield, CA | UIC | 2020-06-25 | Delay Project By Project review data submission. | Chevron would like to request an extension for the data submission of the Kern River UIC PxP Review per the timeline below. 1. WD Project (Vedder/Walker) - March 2021 2. WD Project (Kern River) - March 2021 3. GD Project (Kern River) - June 2021 4. SF/CS Project (Kern River/Chanac) - TBD | No | Partially Approved
44 | Dole Enterprises | Fruitvale & Rosedale | UIC | 2020-06-29 | Delay Project By Project review data submission. | Operator requested an extension of data submission for Dole Enterprises' UIC project updates – 25609022 and 62406001. | No | Approved
45 | Signal Hill Petroleum | Signal Hill, CA | UIC | 2020-05-20 | Delay continuous pressure monitoring. | Request for deadline extension of continuous pressure monitoring system to April 1, 2023. | Yes | Denied
46 | Berry Corporation | Placerita | UIC | 2020-07-08 | Delay well remediation. | Request an extension of the deadline to September 30, 2020 to complete the remedial work, and successfully test the Pryor WD-7 well, per the specifications outlined in the CalGEM NOV and regulations. | Yes | Approved
47 | Berry Corporation | Placerita | UIC | 2020-07-08 | Delay well remediation. | Request an extension of the deadline to November 30, 2020 to complete the remedial work and successfully test the Sedlacek 6 well, per the specifications outlined in the CalGEM NOV and regulations. | Yes | Approved
48 | HVI Cat Canyon, Inc. | Zaca Field, Union Sugar | UIC | 2020-07-08 | Delay Project By Project review data submission. | Request formal approval for a 30-day extension on the Zaca Field Monterey North Block (Zaca) UIC from July 31 to Aug. 31, 2020 and a 30-day extension on the Union Sugar UIC from Aug. 31 to Sept. 30, 2020. | No | Approved
49 | HVI Cat Canyon, Inc. | Richfield Oil Field | UIC | 2020-07-08 | Delay Project By Project review data submission. | Request formal approval for an extension on the REDU Richfield Oil Field UIC (598-00-004) to July 31, 2020. | No | Approved
50 | The Termo Company | Long Beach Airport Field | Pipeline | 2020-05-20 | Delay pipeline testing. | Request a 90-day extension to August 13, 2020 to conduct testing for the Blum, Gallagher, McKenzie, Nakamura, and Olive Community leases in the Long Beach Field and for the Long Beach Fee lease in the Long Beach Airport field. | Yes | Denied
51 | Bridge Energy LLC | Brea-Olinda Field | Pipeline | 2020-06-08 | Delay submission of pipeline management plan (PMP). | Bridge Energy requested a 90-day extension (to September 28, 2020) to submit the revised PMP | Yes | Approved
52 | California Resources Corporation | Wilmington Field | Pipeline | 2020-06-15 | Delay pipeline testing. | CRC submitted this request on behalf of Tidelands Oil Production Co. Request for extension on conducting pipeline hydrotests for six oil gathering lines in the Wilmington field. | Yes | Denied
53 | E&B Natural Resources | 1608 Norris Road, Bakersfield, CA 93308 | UIC | 2020-07-30 | Delay continuous pressure monitoring. | Revised Request. E&B requests deadline extension for continuous pressure monitoring from April 1, 2021 to April 1, 2022. | Yes | Partially Approved
54 | E&B Natural Resources | 1608 Norris Road, Bakersfield, CA 93308 | Idle Well | 2020-07-30 | Idle Well Management Plan (IWMP) extension length | Operator is requesting a deferment of the compliance due date of the 2020 IWMP until July 1, 2021. | Yes | Under Consideration
55 | E&B Natural Resources | 1608 Norris Road, Bakersfield, CA 93308 | Idle Well | 2020-07-30 | Idle Well Testing Compliance Work Plan (CWP) extension length | Request a variance on idle well testing benchmark for the second year of the Testing Compliance Work Plan (CWP). The testing benchmark for 2020 remains 5 percent of all the wells covered by the CWP, and re-assess CWP in April 2021 to set a future schedule. | Yes | Under Consideration
56 | California State Lands Commission | Elwood South, Coastal | UIC | 2020-07-31 | Delay Mechanical Integrity Testing (MIT) schedule. | Request for deadline extension of mechanical integrity testing part two on water disposal well API 28320036 from October 2020 to October 2021. | Yes | Approved
57 | EnviroTech Consultants, Inc. | Fruitvale Oil Field | UIC | 2020-08-17 | Delay Project By Project review data submission. | Operator requested the extension of data submission for Fruitvale UIC project update (UIC Project#25609020 Water Disposal). Plan to submit the update by 10/29/2020. | No | Approved
58 | Krummrich Engineering Corporation | Santa Maria Valley, Coastal | UIC | 2020-08-25 | Extend Temporary Approval for Injection. | Operator requested the extension of temporary approval to inject the produced water from wells Escolle G2 and G4 into the disposal well SMV 402-I (0408322804) until February 26, 2021. | No | Denied
59 | E&B Natural Resources | 1608 Norris Road, Bakersfield, CA 93308 | UIC | 2020-09-29 | Delay continuous pressure monitoring. | E&B requests deadline extension for continuous pressure monitoring from April 1, 2021 to April 1, 2022 with updated well list for 191 wells. | Yes | Partially Approved
60 | E&B Natural Resources | 1608 Norris Road, Bakersfield, CA 93308 | Idle Well | 2020-08-17 | Idle Well Management Plan (IWMP) extension length | Operator is requesting a deferment of the compliance due date of the 2020 IWMP until July 1, 2021. | Yes | Approved
61 | The Termo Company | Oak Canyon, Mountain View Oil, Ojai, Aliso Canyon, South Mountain, Long Beach Fields | UIC | 2020-10-09 | Delay Project By Project review data submission. | The Termo Company updated their requested extension due dates for several UIC project data submission. (Project No. 49006004, Project No. 5201705, Project No. 0100007, Project No. 714003, Project No. 41400001) | No | Approved
62 | EnviroTech Consultants, Inc. | Fruitvale Oil Field | UIC | 2020-10-29 | Delay Project By Project review data submission. | Operator requested an extension of data submission for Fruitvale UIC project update (UIC Project#25609020 Water Disposal). Plan to submit the update by 12/18/2020. | No | Approved
63 | EnviroTech Consultants, Inc. | Fruitvale Oil Field | UIC | 2020-10-29 | Delay Project By Project review data submission. | Operator requested an extension of data submission for Fruitvale UIC project update (UIC Project#25609016 Water Disposal). Plan to submit the update by 02/26/2021. | No | Approved
64 | Krummrich Engineering Corporation | Santa Maria Valley, Coastal | UIC | 2020-09-30 | Extend Temporary Approval for Injection. | Operator requested the extension of temporary approval to inject the produced water from wells Escolle G2 and G4 into the disposal well SMV 402-I (0408322804) for the remaining approved volume of 41,580 bbls. | No | Approved